## Sheet1
The gantt chart for each of deliverables by division.
|  |  | DR. SyRS SD/SDD/ED |  | DR. SwRS SDD/ED |  | DR. SwDD SDD/ED |  | DR. Software SD/SDD/ED |  |  | DR. Closing #1 SD/SDD/ED |  | DR. SyRS SD/SDD/ED |  | DR. SwRS SDD/ED |  | DR. SwDD SDD/ED |  | DR. Software SD/SDD/ED |  |  | DR. Closing #2 SD/SDD/ED
Division | Deliverable
SD (System Division) | SyRS
SDD (Software Development Division) | SwRS
|  |  | A. SyRS | D.SwRS | [9 empty] | A. SyRS | D.SwRS
SwDD
[5 empty] | A. SwRS | D.SwDD | [9 empty] | A. SwRS | D.SwDD
Software ST (Smoke Test)
[7 empty] | A.SwDD | Coding | Smoke Test |  |  |  | Debugging |  |  |  |  | A.SwDD | Coding | Smoke Test |  |  |  | Debugging
ED (Evaluation Division) | UT (Unit Test)
[7 empty] | A.SwDD | D.UT |  | UT | [7 empty] | A.SwDD | D.UT |  | UT
IT (Integrated Test)
[5 empty] | A. SyRS | D.IT |  |  |  |  | IT |  |  |  |  | A. SyRS | D.IT |  |  |  |  | IT
AT (Acceptance Test)
|  |  | A. SyRS | D.UT | [7 empty] | AT |  | A. SyRS | D.UT | [7 empty] | AT
Time→
SyRS (System Requirement Specification) |  |  | Sprint #1
SwRS (Software Requirement Specification)
SwDD (Software Detailed Design) |  |  | Sprint #12
A. (Analysis)
DR. (Design Review) |  |  | Sprint #3